Unapproved IEEE-SA/802 Task Force Minutes

- Wednesday March 14th 1-3pm

- Start Time - 1:00

- Adjourned - 2:43

- Attendees:  Clyde Camp, John Hawkins, Kim Breitfelder,  Michelle Turner, Paul Nikolich, Bob Grow, David Law, Glenn Parsons, Jon Rosdahl, Buzz Rigsbee, Karen Kenney, Steve Mills

- 1) Ombudsman feedback -Kenney  - no new updates – less than 100 hits – will keep running

- 2)Get IEEE 802™ update -Hawkins/Kenney –

- Hawkins – meeting with Karen to discuss costs and  brainstorm
      	3)IEEEAudit Committee Response : Hawkins is preparing a response for approval by EC

- 4)Attendance Software update – Camp – v9 spec will be ready Dec 15th. 802.11 and .15 will be Beta testers

- Action Item: Camp to Consider adding the spec affiliation requirement into IMAT system

- Milestones:

- July 07 Alpha  .11.15

- Sep 07 Beta .11.15

- Nov 07 Beta all of 802

- Mar 08 Production

- Mar 09 Mandatory Use

    - 5)ITU-T Joint Workshop May 2007 – ITU and 802.1,.3 and .17

- Parsons – 300 attendees potentially

- Runs May 31st and June 1st

- 5 Sessions:

- 1. Access

- 2. Ethernet Transport

- 3. Ethernet Bridging

- 4. Management

- 5. Synchronization

- 6) myBallot/myProject update – Kipness – Spoke about Manage Committee link and P&Ps into myProject