## Action Items from Nov Workshop
EC-12/03r1 |  | November 2011 IEEE 802 EC Workshop Action Item Register;
AI ID | Who | Due Date | Action Item description | Status | Reported complete
WS11-1 | Kraemer | 2012-01-10 | Get Letter to SC6 posted Prepared an EC ballot with time to post final letter to SC6 Get Input from Edit committee and other EC members | Done -- Letter sent to SC6 and posted to 802EC Mentor: https://mentor.ieee.org/802-ec/dcn/12/ec-12-0001-01-00EC-liaison-to-sc6-re-8802-standards.doc
WS11-2 | Rosdahl | 2012-01-31 | Prepare a list of all the Booked and Contracted venues for Plenaries and a list of open dates within the next 5 years. | 2012-2014 Public listing: http://802world.org/plenary/future-plenary-sessions/ See Tab WS11-2
WS11-3 | Rosdahl | 2012-01-31 | Evaluation of 2014 venues for potential Non-North America venue substitution. | Current Assignment is to move one of the currently scheduled 2014 events and schedule Singapore in its place for 2014.
WS11-4 | Rosdahl | 2012-01-31 | Prepare a proposal for a rule change ballot to provide guidance for future regional choice of venues. (Ballots to close with sufficient time to allow the proposal to be presented for final approval in the 802 EC Closing Plenary in March)
WS11-5 | Rosdahl | 2012-01-31 | Prepare a proposal for a rule change ballot to require venue selection be approved by the EC prior to contract signing. (Ballot to close with sufficient time to allow the proposal to be presented for final approval in the 802 EC Closing Plenary in March)
WS11-6 | Gilb | 2012-01-31 | Create a proposed plan for how the e-tools can go into open source.
WS11-7 | Law | 2012-01-31 | Setup a meeting to discuss with the SA–Open Application Interfaces, and Open source.
WS11-8 | Diab | 2012-01-31 | Identify a proces with staff to prioritize and discuss Frame version transitions.
WS11-9 | Sherman | 2012-01-31 | Add to Chair's Guideline an explaination of Tutorial registration requirement: No registration required -- No Fee -- No other WG meetings to be held in parrallel during Monday night Tutorials.
WS11-10 | Nikolich | 2012-01-31 | Work with the SA to reduce the 802 Standards price point | Announced 2-2-2012 -- 802 Standards available for $5. http://www.standardsinsight.com/ieee_news/802sale2012
WS11-11 | Diab / Law | 2012-01-31 | Start a dialog with the CAG about updating the SASB operation manual to allow for joint Entity and Individual balloting.
WS11-12 | All WG Chairs | 2012-01-31 | Review attendance rolls and for all affiliations that are obviously not valid, should be reported to the SASB Secretary
WS11-13 | Rosdahl | 2012-01-31 | Add a ticket for IMAT to not use the word "Affiliation" on the main login page -- changing the wording in the instructions (see screenshot from Roger) | Imat Ticket #1016
WS11-14 | Nikolich | 2012-01-31 | Setup a discussion with SA senior staff to specify the IEEE 802 IEEE-SA Standards Service provider relationship | ongoing -- Regular meetings every 6 weeks (Nikolich/McCabe)
WS11-15 | Rosdahl | 2012-01-31 | Post report of Tool Error from AI-14-Nov-11 | Report still pending. Tool Errors for the Week of the Plenary are to be reported.
WS11-16 | Rosdahl | 2012-01-31 | Report on Session Expectation Criteria -- Poll WG chairs on the following: Max Session fee tolerance, Min Service expecation, location rotation expectations, Session fee leveling tolerance (some Sessions have surplus, some do not). | poll sent out on 2-3-2012
WS11-17 | Diab | 2012-01-31 | Create an ADHOC to prepare material for "WG VC to vote during EC meetings in the absense of the WG Chair" for the Feb Telcon and have material ready for March. (Adhoc members: Jon, Rakesh, Roger, Bruce, David and Matthew) | Telecon held 30Jan2012.
WS11-18 | Gilb | 2012-12-01 | Update the home page for the public vs EC information. Update the initial statement to match the Scope in the P&P.
WS11-19 | Sherman | 2012-01-31 | Prepare proposal for updating the Scope statement in the P&P.
WS11-20 | Kraemer | 2012-01-31 | make a list of what 802 projects and standards that operate above layer 2. | More difficult and controversial than expected. Needs more discussion time in Waikoloa. Candidates include 802.21, 802.1X (management plane comprehends layer 3),others?
WS11-21 | Jeffree | 2012-01-31 | Internal statement – O&A about what the scope of projects in 802 are – ensure that it is consistent with P&P
WS11-22 | Marks | 2012-01-31 | Adhoc: Prepare a proposal for changing LMSC OM 12.5.2 Compatibility to specify a specific procedural element to that criterion. | See Tab WS11-22
WS11-23 | Rosdahl | 2012-03-01 | Report on the status of the EC Workshop Action items. | Action item file posted to 802EC Mentor: see doc ec-12/3r1 for updated status.
WS11-24 | Sherman | 2012-01-31 | Prepare a Rule change for clarifying the WG term limitation exemption starting with EC Chair interpertation email.
WS11-25 | Sherman | 2012-01-31 | Prepare a Rule change for clarifying the recirculation requirement following a conditional approval starting with the EC Chair Interpretation email.
WS11-26 | Rosdahl | 2012-01-31 | Identify possible venues that can host the future Workshop. | Target is Nov 2013 Dallas
WS11-27 | Law | 2012-03-01 | Actually from Nov 2012 Closing Plenary: Univerisity Outreach: how can we encourage participation in Standards activities by University students? | Draft recommendation is being prepared for circulation. (2 AdHoc Calls have been held).

## WS11-2
IEEE 802 Plenary Meeting Contract Tracker
Year | Month | Session START | Session END | Session Type | IEEE Region | Host ? YES/NO | Host Name | Country | City | State / Province | Event Venue | Meeting Planner Contract Status | Notes/Comments | Document Updated | IEEE contract #
2012 | March | 11 | 16 | Plenary | Asia & Pacific | NO |  | USA | Waikoloa | Hawaii | Hilton Waikoloa Village | Confirmed
2012 | July | 15 | 20 | Plenary | North America | NO |  | USA | San Diego | California | Manchester Grand Hyatt | Confirmed
2012 | November | 11 | 16 | Plenary | North America | NO |  | USA | San Antonio | Texas | Grand Hyatt San Antonio | Confirmed
2013 | March | 17 | 22 | Plenary | North America | NO |  | USA | Orlando | Florida | Caribe Royale Resort | Confirmed |  |  | # 09-4250-13
2013 | July | 14 | 19 | Plenary | Europe | NO |  | SWITZERLAND | Geneva |  | ITU | Contract Pending | MOU in development stage, SWAG Budget due February 3, 2012
2013 | November | 10 | 15 | Plenary | North America | NO |  | USA | Dallas | Texas | Hyatt Regency Dallas | Confirmed |  |  | # 09-4217-13
2014 | March | 16 | 21 | Plenary | North America | NO |  | USA | Atlanta | Georgia | Hyatt Regency Atlanta | Confirmed
2014 | July | 13 | 18 | Plenary | North America | NO |  | USA | San Diego | California | Manchester Grand Hyatt | Confirmed
2014 | November | 2 | 7 | Plenary | North America | NO |  | USA | San Antonio | Texas | Grand Hyatt San Antonio | Confirmed |  |  | # 09-4219-14
2104 | TBD - M/J/N ? |  |  | Plenary | Asia/Pacific | Yes |  | Singapore | Singapore |  |  | Tenative
2015 | March |  |  | Plenary
2015 | July |  |  | Plenary
2015 | November |  |  | Plenary | North America | NO |  | USA | Dallas | Texas | Hyatt Regency Dallas |  |  |  | # 09-4218-15
2016 | March |  |  | Plenary
1016 | July |  |  | Plenary
2016 | November | 3 | 15 | Plenary | North America | NO |  | USA | San Antonio | Texas | Grand Hyatt San Antonio |  |  |  | # 09-4220-16
2017 | March
2017 | July
2017 | November

## WS11-22
Marks 12/01/31 Adhoc: Prepare a proposal for changing LMSC OM 12.5.2 Compatibility to specify a specific procedural element to that criterion.
Tony has joined the ad hoc group. He and I are proposing the following change:
--------------
Current:
12.5.2 Compatibility
IEEE 802 LMSC defines a family of standards. All standards should be in conformance with the IEEE 802.1 Architecture, Management, and Interworking documents as follows: IEEE 802.1 Overview and Architecture, IEEE 802.1D, IEEE 802.1Q, and parts of IEEE 802.1F. If any variances in conformance emerge, they shall be thoroughly disclosed and reviewed with IEEE 802.1.
Each standard in the IEEE 802 LMSC family of standards shall include a definition of managed objects that are compatible with systems management standards.
Proposed:
12.5.2 Compatibility
IEEE 802 LMSC defines a family of standards. All standards should be in conformance with IEEE Std 802, IEEE Std 802.1D, and IEEE Std 802.1Q. If any variances in conformance emerge, they shall be thoroughly disclosed and reviewed with the IEEE 802.1 Working Group.
In order to demonstrate compatibility with this criterion, the Five Criteria statement must answer the following questions:
*Does the PAR mandate that the standard will comply with IEEE Std 802, IEEE Std 802.1D, and IEEE Std 802.1Q?
*If not, how will the Working Group ensure that the resulting draft standard is compliant or, if not, receives appropriate review from the IEEE 802.1 Working Group?
--------------
Please let me know if you have comments or would like to participate in followup email discussions. Write to Tony and me; I don't see a need to copy everyone at this time. I'll make sure we get something ready by the deadline so the EC has an opportunity, at the Feb telecon, to decide to open a rules change ballot.
Roger